PLAN OF WORK ON DISSERTATION

PhD student’s name: Muwaffaq Imam

Year of study: 4th year (PhD)

Research supervisor: Evgenii Zuev

Dissertation (thesis) topic: Large Language Models in Islamic Jurisprudence: A Multi-Method Framework for Hadith Authentication and Hanafi Fatwa Synthesis

| № | Activity | Dates (January,12 – May,10) | Details |
| --- | --- | --- | --- |
| 1 | Finalization of the doctoral dissertation manuscript (Agentix Islam framework). | January 12 – February 10, 2026 | Consolidated chapters R1–R6 into a unified Thesis_Master document, harmonized notation, completed Introduction (Relevance, Novelty, Objectives), built unified BibTeX bibliography, and produced the compiled PDF of the dissertation. |
| 2 | Preparation of the Scientific Report (Научный доклад). | February 11 – March 5, 2026 | Drafted the expanded Scientific Report summarizing the main results of the dissertation: 12 sections covering Relevance, Novelty, Methodology, Propositions for Defense, Publications, and Reliability of Results. |
| 3 | Completion of Research Track R3 — Ahadith Authenticity Dataset. | March 6 – March 25, 2026 | Finalized the bilingual (Arabic–English) structured dataset of 1,896 Hadiths from Riyad al-Salihin, with Sanad/Matn separation and expert theological validation by Sheikh Omar; prepared the dataset release on Kaggle. |
| 4 | Completion of Research Track R5 — Hanafi Fatwa LLM Benchmark. | March 26 – April 10, 2026 | Conducted the 'LLM-as-a-Judge' benchmark of state-of-the-art models (GPT-5, Gemini 2.5) against a 10,000-pair gold-standard Hanafi Fatwa dataset; quantified Generative Doctrinal Failure and authored the corresponding paper draft. |
| 5 | Completion of Research Track R6 — Agentix Islam RAG System. | April 11 – April 30, 2026 | Deployed the Agentix Islam framework (FastAPI + Chroma DB + Gemini 3 Flash) with TOC Hierarchy Mapping, MMR retrieval and Cohere v3.0 reranking; system served 4,000 live user queries with zero doctrinal failures. |
| 6 | Publications, conference participation and pre-defense activities. | May 1 – May 10, 2026 | Presented two papers at KES-AMSTA 2025 (Scopus-indexed); submitted a journal article on the Fatawa AI benchmark; prepared two technical reports for the University Scientific Council and the IP registration package for the Agentix Islam API. |

PhD student   _____________       /Muwaffaq Imam/

Research supervisor   _____________       /Evgenii Zuev/

Date  10.05.2026